## Ark1
Project Exam 1 |  |  | Planning |  |  |  |  | Interaction Design |  |  |  |  | JS/HTML/CSS |  |  |  |  | JS (HTML/CSS) |  |  |  |  | Report
Start date: 08.24.2020 - End date: 09.27.2020 |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5
Milestones | % | Days | 08.24 Monday | 08.25 Tuesday | 08.26 Wednesday | 08.27 Thursday | 08.28 Friday | 08.31 Monday | 09.01 Tuesday | 09.02 Wednesday | 09.03 Thursday | 09.04 Friday | 09.07 Monday | 09.08 Tuesday | 09.09 Wednesday | 09.10 Thursday | 09.11 Friday | 09.14 Monday | 09.15 Tuesday | 09.16 Wednesday | 09.17 Thursday | 09.18 Friday | 09.21 Monday | 09.22 Tuesday | 09.23 Wednesday | 09.24 Thursday | 09.25 Friday
Create a Gantt chart | % | 1
Getting an overview,select an API and choose target audience | % | 1
Design research | % | 1
Creating personas and scenarions | % | 2 (+1)
Find out context, platforms, info architecture | % | 2 (+1)
Low fidelity prototyping, mockup | % | 2 (+2)
Find out the mood board, colours, fonts, images/videos | % | 1 (+1)
Principles of interaction design | % | 1 (+1)
Wireframing | % | 3
API calls | % | 1 (+1)
Global style | % | 2 (+1)
Mobile devices | % | 1(+1)
Tablet devices | % | 1 (+1)
Desktop devices | % | 1 (+1)
Form validation | % | 1 (+3)
Javascript on various pages | % | 2 (+2)
Javascript on various pages | % | 2 (+1)
Javascript on various pages | % | 2 (+1)
Testing / debugging? | % | 1 (+4)
Planning phase | % | 1 (+5)
Interaction design phase | % | 1 (+5)
Coding phase | % | 1 (+7)
Introduction and conclusion | % | 1 (+2)
Resources, detailed review | % | 1 (+1)